## Daily Gantt Chart Template
DAILY GANTT CHART
[7 empty] | Shakeel Ali | [14 empty] | 2022-09-30 | 2022-10-14
Information Systems 722: Data Mining and Big Data Project | [6 empty] | Student Name | [14 empty] | START DATE | END DATE
Task ID | Task Category | Task Name | Start Date | End Date | Duration (In Days) | 2022-09-30 | 31/09/2022 | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14
1 | Business Understanding |  | 2022-09-30 | 2022-09-30 | 1
1.1 | Business Understanding | Business/Situation Objectives | 2022-09-30 | 2022-09-30 | 0
1.2 | Business Understanding | Assessment of the Situation | 2022-09-30 | 2022-09-30 | 0
1.3 | Business Understanding | Data Mining Objectives | 2022-09-30 | 2022-09-30 | 0
1.4 | Business Understanding | Project Plan | 2022-09-30 | 2022-09-30 | 0
2 | Data Understanding |  | 31/09/2022 | 31/09/2022 | 1
2.1 | Data Understanding | Collecting Initial Data | 31/09/2022 | 31/09/2022 | 0
2.2 | Data Understanding | Describing Data | 31/09/2022 | 31/09/2022 | 0
2.3 | Data Understanding | Data Exploration | 31/09/2022 | 31/09/2022 | 0
2.4 | Data Understanding | Verifying Data Quality | 31/09/2022 | 31/09/2022 | 0
3 | Data Preparation |  | 2022-10-01 | 2022-10-04 | 5 | bar: 2022-10-01 to 2022-10-04
3.1 | Data Preparation | Data Selection | 2022-10-01 | 2022-10-01 | 1 | bar: 2022-10-01
3.2 | Data Preparation | Data Cleaning | 2022-10-01 | 2022-10-02 | 2 | bar: 2022-10-01 to 2022-10-02
3.3 | Data Preparation | Constructing/Deriving a new feature | 2022-10-03 | 2022-10-03 | 1 | bar: 2022-10-03
3.4 | Data Preparation | Data Integration | 2022-10-04 | 2022-10-04 | 1 | bar: 2022-10-04
3.5 | Data Preparation | Formatting Data | 2022-10-04 | 2022-10-04 | 0 | bar: 2022-10-04
4 | Data Transformation |  | 2022-10-05 | 2022-10-07 | 2 | bar: 2022-10-05 to 2022-10-07
4.1 | Data Transformation | Data Reduction | 2022-10-05 | 2022-10-06 | 1 | bar: 2022-10-05 to 2022-10-06
4.2 | Data Transformation | Data Projection | 2022-10-07 | 2022-10-07 | 1 | bar: 2022-10-07
5 | Data Mining Method(s) Selection |  | 2022-10-08 | 2022-10-08 | 1 | bar: 2022-10-08
5.1 | Data Mining Method(s) Selection | Matching Objectvies to Mining Method(s) | 2022-10-08 | 2022-10-08 | 0 | bar: 2022-10-08
5.2 | Data Mining Method(s) Selection | Selection of Data Mining Method(s) | 2022-10-08 | 2022-10-08 | 0 | bar: 2022-10-08
6 | Data Mining Algorithm(s) Selection |  | 2022-10-08 | 2022-10-08 | 1 | bar: 2022-10-08
6.1 | Data Mining Algorithm(s) Selection | Exploratory Analysis of Data-Mining Algorithms | 2022-10-08 | 2022-10-08 | 0 | bar: 2022-10-08
6.2 | Data Mining Algorithm(s) Selection | Selecting Algorithm(s) based on Discussion and Exploratory Analysis | 2022-10-08 | 2022-10-08 | 0 | bar: 2022-10-08
6.3 | Data Mining Algorithm(s) Selection | Building/Selecting Model with Algorithm/Model Parameter(s) | 2022-10-08 | 2022-10-08 | 0 | bar: 2022-10-08
7 | Data Mining |  | 2022-10-09 | 2022-10-11 | 3 | bar: 2022-10-09 to 2022-10-11
7.1 | Data Mining | Creating Logical Test(s) | 2022-10-09 | 2022-10-09 | 1 | bar: 2022-10-09
7.2 | Data Mining | Conducting Data Mining (Running the model) | 2022-10-10 | 2022-10-10 | 1 | bar: 2022-10-10
7.3 | Data Mining | Searching for Patterns | 2022-10-11 | 2022-10-11 | 1 | bar: 2022-10-11
8 | Interpretation |  | 2022-12-12 | 2022-10-14 | 3 | bar: 2022-10-12 to 2022-10-14
8.1 | Interpretation | Study and Discuss Mined Patterns | 2022-12-12 | 2022-12-12 | 1 | bar: 2022-10-12
8.2 | Interpretation | Visualization of the Data, Results, Models and Patterns | 2022-12-13 | 2022-12-13 | 0 | bar: 2022-10-13
8.3 | Interpretation | Interpreting the Results, Models and Patterns | 2022-12-13 | 2022-12-13 | 1 | bar: 2022-10-13
8.4 | Interpretation | Assessing and Evaluating Results, Models and Patterns | 2022-12-14 | 2022-12-14 | 1 | bar: 2022-10-14
8.5 | Interpretation | Iteration of steps 3.1 to 8.4 | 2022-12-14 | 2022-12-14 | 0 | bar: 2022-10-14

## ©
© TemplateLab.com